## Folha1
Date | Assignment | Milestone | entrega trabalhos/exames
2020-03-09 | Introduction to docker, react, bash, python
2020-03-16 | Set up DB, webserver react configuration, Environment JVM | Project Proposal 16 Mar
2020-03-23 | Set up DB, webserver react configuration, Environment JVM
2020-03-30 | Environment JVM, Environment Node, Execute code page
2020-04-06 | Environment JVM,Environment Node, Execute code page
2020-04-13 | Environment JVM, Environment Node, Home Page |  | 20 Abril Entrega trabalho 1 DAW
2020-04-20 | Progress Report and Individual presentation
2020-04-27 | Progress Report and Individual presentation
2020-05-04 | Chanllenges service, Home Page, User Services | Progress Report and Individual presentation 4 May
2020-05-11 | Challenges service, User Services, Questionnaire service
2020-05-18 | Challenges service, User Profile Page, Questionnaire service
2020-05-25 | Poster and Beta version, Questionnaire service
2020-06-01 | Challenges service, User Profile Page, Questionnaire service | Poster and Beta version 1 June
2020-06-08 | Login Signin Page, Questionnaire Fill Page, Auth Service
2020-06-15 | Login Signin Page, Questionnaire Fill Page, Auth Service
2020-06-22 | Exams
2020-06-29
2020-07-06
2020-07-13
2020-07-20
2020-07-27 | Challenge Page, Environment Python, Environment CLR
2020-08-03 | Challenge Page, Environment Python, Environment CLR
2020-08-10 | Challenge Page, Environment Python, Environment CLR
2020-08-17 | Cloud environment deployment
2020-08-24 | Cloud environment deployment
2020-08-31 | Wrap up final report
2020-09-07 | Wrap up final report | Final delivery 12 Sept
Formulas:
Date = +[Date, row above]+7