## Folha1
Date | Assignment | Milestone | entrega trabalhos/exames
2020-03-09 | Introduction to docker, react, bash, python
2020-03-16 | Set up DB, webserver react configuration, E(JVM) | Project Proposal 16 Mar
2020-03-23 | Set up DB, webserver react configuration, E(JVM)
2020-03-30 | E(JVM), E(Node), P(Execute code)
2020-04-06 | E(JVM), E(Node), P(Execute code)
2020-04-13 | E(JVM), E(Node), P(Home) |  | 20 Abril Entrega trabalho 1 DAW
2020-04-20 | Progress Report and Individual presentation
2020-04-27 | Progress Report and Individual presentation
2020-05-04 | S(Challenges), P(Home), S(User) | Progress Report and Individual presentation 4 May
2020-05-11 | S(Challenges), S(User), S(Questionnaire)
2020-05-18 | S(Challenges), P(User's Profile), S(Questionnaire)
2020-05-25 | Poster and Beta version, S(Service)
2020-06-01 | S(Challenges), P(User's Profile), S(Questionnaire) | Poster and Beta version 1 June
2020-06-08 | P(Login and Signin ), P(Fill Questionnaire), S(Authentication)
2020-06-15 | P(Login and Signin ), P(Fill Questionnaire), S(Authentication)
2020-06-22 | Exams |  | epoca exames
2020-06-29
2020-07-06
2020-07-13
2020-07-20
2020-07-27 | P(Challenge), E(Python), E(CLR)
2020-08-03 | P(Challenge), E(Python), E(CLR)
2020-08-10 | P(Challenge), E(Python), E(CLR)
2020-08-17 | Cloud environment deployment
2020-08-24 | Cloud environment deployment
2020-08-31 | Wrap up final report
2020-09-07 | Wrap up final report | Final delivery 12 Sept
|  |  |  | Assignment Type | Description
|  |  |  | E(x) | Design, Implementation and deploying to the cloud of a solution capable of running code "remotely"
|  |  |  | P(x) | Creation of webpage
|  |  |  | S(x) | Design and Implementation of backend service
Formulas:
Date = +[Date, row above]+7