## Folha1
Date | Assignment | Milestone | entrega trabalhos/exames
2020-03-09 | Introduction to docker, react, bash, python
2020-03-16 | Set up DB, Environment CLR + Node, Environment JVM | Project Proposal 16 Mar
2020-03-23 | Set up DB, Environment CLR + Node, Environment JVM
2020-03-30 | Environment CLR + Node, Environment JVM, Python Environment
2020-04-06 | Environment CLR + Node, Environment JVM,
2020-04-13 | Environment CLR + Node, Environment JVM, |  | 20 Abril Entrega trabalho 1 DAW
2020-04-20 | Progress Report and Individual presentation
2020-04-27 | Progress Report and Individual presentation
2020-05-04 | Runtime CLR + Node, Python Environment, Question MS | Progress Report and Individual presentation 4 May Environments
2020-05-11 | Challenge MS, Python Environment , Webserver react configuration
2020-05-18 | Challenge MS, Python Environment , Webserver react configuration
2020-05-25 | Poster and Beta version
2020-06-01 | Challenge MS, Questionnaire MS, UsersMS | Poster and Beta version 1 June
2020-06-08 | Questionnaire MS, UsersMS, Question Page | MS
2020-06-15 | Questionnaire MS Home page , User profile page, Question Page
2020-06-22 | Exams |  | epoca exames
2020-06-29
2020-07-06
2020-07-13
2020-07-20
2020-07-27 | Questionnaire MS Home page , User profile page, Question Page
2020-08-03 | Home page , User profile page, Question Page
2020-08-10 | Home page , User profile page, Edit/Create Questionnaire Page
2020-08-17 | Login and Sign in , Questionnaire submit, Edit/Create Questionnaire Page
2020-08-24 | Login and Sign in , Questionnaire submit, Edit/Create Questionnaire Page
2020-08-31 | Wrap up final report
2020-09-07 | Wrap up final report | Final delivery 12 Sept
Formulas:
Date = +[Date, row above]+7